## Sheet9
Division Wise Approved Action Plan National Food Security Mission -Pulses Rabi 2014-15 & Progress made as on 1-04-2015 In respect of Jammu& Kashmir State ( Fin. Rs. In Lakhs)
S.No | Interventions | Approved Rate of Assistance | Unit | Jammu |  |  |  | Kashmir |  |  |  | J&KState
|  |  |  | Approved Action Plan |  | Achievement as on 1-04-2015 |  | Approved Action Plan |  | Achievement as on 1-04-2015 |  | Approved Action Plan |  | Achievement as on 1-04-2015
|  |  |  | Phy. | Fin. | Phy. | Fin. | Phy. | Fin. | Phy. | Fin. | Phy. | Fin. | Phy. | Fin.
1 | Demonstrations on Improved Technologies: (a) Cluster Demonstrations ( of 100 ha each) | Rs.7500/ha | ha | 100 | 7.5 | 100 | 3.7126 | 0 | 0 | 0 | 0 | 100 | 7.5 | 100 | 3.7126
2 | Distribution of Seeds: HYV Seeds | Rs. 2500/=/qtl. | qtl. | 150 | 3.75 | 0 | 0 | 1560 | 39 | 525.2 | 13.13 | 1710 | 42.75 | 525.2 | 13.13
3 | Integrated Pest Management (IPM)
| (a) Distribution of PP Chemicals | Rs.500/ha | ha | 825 | 4.125 | 126 | 0 | 500 | 2.5 | 0 | 0 | 1325 | 6.625 | 126 | 0
| (b) Weedicides | Rs. 500/ha | ha | 715 | 3.575 | 0 | 0 | 500 | 2.5 | 0 | 0 | 1215 | 6.075 | 0 | 0
| Sub- Total 3(a) to (3(b) |  |  | 1540 | 7.7 |  | 0 | 1000 | 5 | 0 | 0 | 2540 | 12.7 | 0 | 0
4 | Integrated Nutrient Management (INM) | [12 empty] | 0 | 0
| Distribution of Micro nutrients | Rs. 500/= per Ha | ha | 0 | 0 | 0 | 0 | 500 | 2.5 | 0 | 0 | 500 | 2.5 | 0 | 0
| Distribution of Bio- Fertilizers | Rs. 100/= per ha | ha | 0 | 0 | 0 | 0 | 500 | 0.5 | 0 | 0 | 500 | 0.5 | 0 | 0
| Sub-Total 4 (a) to 4(b) |  |  | 0 | 0 | 0 | 0 | 1000 | 3 | 0 | 0 | 1000 | 3 | 0 | 0
5 | Resource Conservation Technologies/Tools:
| a)Mannual Sprayer | Rs. 600/= per unit | Nos. | 0 | 0 | 0 | 0 | 500 | 3 | 0 | 0 | 500 | 3 | 0 | 0
| b) Rotavator | Rs. 35000/unit | Nos. | 15 | 5.25 | 5 | 0 | 0 | 0 | 0 | 0 | 15 | 5.25 | 5 | 0
| Sub-Total 5 (a) to 5(b) |  |  | 15 | 5.25 |  | 0 | 500 | 3 | 0 | 0 | 515 | 8.25 | 0 | 0
6 | Efficient Water Application Tools:
| Pump sets | Rs. 10000/unit | Nos. | 160 | 16 | 55 | 0 | 0 | 0 | 0 | 0 | 160 | 16 | 55 | 0
7 | Cropping System based trainings (Four Sessions i.e. one before Kharif and Rabi seasons, one each during Kharif and Rabi crops) | Rs. 3500/session Rs. 14000/Training | Nos. | 20 | 1.4 | 20 | 0.77 | 0 | 0 | 0 | 0 | 20 | 1.4 | 20 | 0.77
8 | Local Initiatives
| Diesel Plough | 50% subsidy limited to Rs. 0.20 lakhs/no. | Nos. | 35 | 7 | 8 | 0.6 | 0 | 0 | 0 | 0 | 35 | 7 | 8 | 0.6
| Total Financial (1 to 8) |  |  |  | 48.6 |  | 5.0826 |  | 50 |  | 13.13 |  | 98.6 |  | 18.2126
Action Plan Approved |  |  | Funds Released by Adm. Deptt |  |  |  | Utilization
Jammu Division |  | 48.6 | 14.88 |  |  |  | 5.0826
Kashmir Division |  | 50 | 13.13 |  |  |  | 13.13 |  |  |  |  | Director Agriculture
Total |  | 98.6 | 28.01 |  |  |  | 18.2126 |  |  |  |  | Jammu