## Sheet19
DIVISION WISE APPROVED ACTION PLAN AND PROGRESS MADE AS ON 1-04-2015 UNDER CENTRALLY SPONSORED SCHEME NATIONAL FOOD SECURITY MISSION RICE-(NFSM-RICE) FOR THE YEAR 2014-15 IN RESPECT OF JAMMU & KASHMIR STATE
S.No | Interventions | Approved Rate of Assistance | Unit | Jammu Division |  |  |  | Kashmir Division |  |  |  | Approved Plan J&KDivision |  | Achievement of J&K Division as on 1-04-2015
|  |  |  | Approved Plan |  | Achievements as on 1-04-2015 |  | Approved Plan |  | Achievements as on 1-04-2015 |  | J&K Division |  | Achievement as on 1-04-2015
|  |  |  | Phy. | Fin. | Phy. | Fin. | Phy. | Fin. | Phy. | Fin. | Phy. | Fin. | Phy. | Fin.
1 | Cluster Demonstration by State Department of Agriculture with the technical backstopping of ICAR/SAUs/IRRI (One cluster of 100 ha) (Specify the Interventions Proposed To be Demonstrated)
a) | HYV Seed Direct seeded Rice/Line Transplanting /SRI (Target 1.5% of area of District* | Rs7500/-per ha | Ha | 600 | 40.2 | 600 | 34.83 | 900 | 60.3 | 900 | 13.4 | 1500 | 100.5 | 1500 | 48.23
| Sub Total |  |  | 600 | 40.2 |  | 34.83 |  | 60.3 |  | 13.4 | 600 | 100.5 |  | 48.23
2 | Seed Distribution
a) | Hybrid Rice Seed | Rs 5000/-per Qtl | Qtls | 1500 | 75 | 952.2 | 47.61 | 0 | 0 | 0 | 0 | 1500 | 75 | 952.2 | 47.61
b) | High Yielding Variety (HYV) Seeds ** | Rs1000/-per Qtl | Qtls | 0 | 0 | 0 | 0 | 12500 | 125 | 5930.3 | 59.303 | 12500 | 125 | 5930.3 | 59.303
| Sub Total 2(a) and (b) |  |  |  | 75 |  | 47.61 |  | 125 |  | 59.303 |  | 200 |  | 106.913
3 | Plant and Soil Protection Management: | [13 empty] | 0
a) | Micronutrients | Rs 500/-per ha | Ha | 600 | 3 | 600 | 2.9995 | 1400 | 7 | 1000 | 5 | 2000 | 10 | 1600 | 7.9995
c) | Plant Protection Chemicals & bio-agents | Rs 500/-per ha | Ha | 600 | 3 | 600 | 2.9994 | 1400 | 7 | 1000 | 5 | 2000 | 10 | 1600 | 7.9994
d) | Weedicides | Rs 500/-per ha | Ha | 1300 | 6.5 | 1000 | 5 | 6700 | 33.5 | 1700 | 8.5 | 8000 | 40 | 2700 | 13.5
| Sub Total 3 (a) to 3 (e) |  |  |  | 12.5 |  | 10.9989 |  | 47.5 |  | 18.5 |  | 60 |  | 29.4989
4 | Resource Conservation Techniques / Tools
a) | Conoweeder | Rs. 600/ unit | Nos | 0 | 0 | 0 | 0 | 1000 | 6 | 170 | 1.02 | 1000 | 6 | 170 | 1.02
b) | Mannual Sprayer | Rs. 600/ unit | Nos | 50 | 0.3 | 50 | 0.3 | 0 | 0 | 0 | 0 | 50 | 0.3 | 50 | 0.3
c) | Power Knap Sack Sprayers | Rs 3000/-per unit | Nos | 0 | 0 | 0 | 0 | 300 | 9 | 156 | 4.66 | 300 | 9 | 156 | 4.66
i) | Rotavators | Rs 35000/-per unit | Nos | 6 | 2.1 | 6 | 2.1 | 50 | 17.5 | 0 | 0 | 56 | 19.6 | 6 | 2.1
| Sub Total 4 (a) to ( d) |  |  | 56 | 2.4 | 56 | 2.4 | 1350 | 32.5 | 326 | 5.68 | 1406 | 34.9 |  | 8.08
5 | Incentive for Pumpsets | Rs10000/-per unit | Nos | 110 | 11 | 106 | 10.4355 | 490 | 49 | 419 | 41.9 | 600 | 60 | 525 | 52.3355
6 | Paddy Thrasher / Multi Crop Planter | Rs. 40000 / ha | ha | 15 | 6 | 15 | 3.2 | 25 | 10 | 14 | 5.54 | 40 | 16 | 29 | 8.74
8 | Cropping System based trainings (Four Sessions one before Kharif, One each during kharif and rabi crops and one after Rabi harvest) | Rs 3500/-Session Rs 14000/-Training | Nos | 10 | 1.4 | 10 | 1.33 | 14 | 1.96 | 0 | 0 | 24 | 3.36 | 10 | 1.33
10 | Local Initiatives
a) | 1. Disel Plough | 50 % subsidy limited to Rs. 0.20 lakhs / no. | Nos | 20 | 4 | 6 | 1.2 | 0 | 0 | 0 | 0 | 20 | 4 | 6 | 1.2
| 2. Construction of Godowns | 50 % subsidy limited to Rs. 0.75 lakhs / no. | Nos | 22 | 16.5 | 17 | 12 | 35 | 26.25 | 8 | 6 | 57 | 42.75 | 25 | 18
| Total Division Wise Fin. Allocation / Achievement |  |  |  | 169 |  | 124.0044 |  | 352.51 |  | 150.323 |  | 521.51 |  | 274.3274
| Synopsis | [5 empty] | Progress made as on 1-04-2015
| Action Plan 2014-15 |  | Rs. 521.51 Lakhs |  |  |  | Rs. 274.32739 Lakhs
| Jammu Division |  | Rs.169.00lakhs |  |  |  | Rs. 124.00439 Lakhs
| Kashmir Divisuion |  | Rs 352.51 Lakhs |  |  |  | Rs. 150.323 Lakhs |  |  |  |  | Director of Agriculture
| * | Assistance restricted to Rs. 6,700/= under Cafteria Interventions | [9 empty] | Jammu
| ** | Seed Varities distributed to be less than ten years | [9 empty] | State Mission Director NFSM